## Daily Tasks
Date | Category | Task | Status | Priority | Pending Work | Developer | Notes
2025-05-29 | Design | Referance Design | Completed | High | Task completed successfully - Ready for next phase | Harish | Completed
2025-05-30 | Authentication | Template Designing | Completed | High | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-02 | API Development | UI Development | Completed | High | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-03 | Authentication | User Registration System | Completed | High | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-04 | Authentication | Login/Logout Functionality,OTP Verification,Course Model Implementation | Completed | High | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-05 | Course Management | Course Creation System, Course Content Upload ,Section & Subsection Management | Completed | High | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-06 | Security | Role-based Access Control ,Input Validation | Completed | Medium | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-07 | Course Management | Course Catalog Interface | Completed | High | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-08 | Frontend | Student Dashboard, Instructor Dashboard, Toast Notifications | Completed | High | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-09 | Authentication | User Management System | Completed | High | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-10 | Course Management | Course Player Interface | Completed | High | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-11 | Development | Cloudinary Integration | Completed | Medium | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-12 | Course Management | Section & Subsection Management | Completed | High | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-13 | Admin Panel | Analytics Dashboard | Completed | Medium | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-14 | Course Management | Course Status Management | Completed | High | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-16 | Course Management | Course Approval System | Completed | High | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-17 | Admin Panel | Admin Dashboard, Admin Panel Features | Completed | High | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-18 | Course Management | Course Access Management | Completed | High | Task completed successfully - Ready for next phase | Harish | Completed
2025-06-19 | Frontend | Responsive Design | Completed | High | Task completed successfully - Ready for next phase | Harish | Completed
| Development | Bug Fixes | Completed | Medium | Task completed successfully - Ready for next phase | Harish | Completed

## Summary
Metric | Value
Report Period | 2025-05-30 to 2025-06-19
Total Days | 21
Total Tasks | 63
Completed Tasks | 60
In Progress Tasks | 3
Pending Tasks | 0
High Priority Tasks | 42
Medium Priority Tasks | 19
Low Priority Tasks | 2
Total Estimated Hours | 302
Total Actual Hours | 301
Average Completion % | 98
Week 1 Tasks | 21
Week 2 Tasks | 21
Week 3 Tasks | 21

## Category Summary
Category | Total Tasks | Completed | In Progress | Pending | Completion %
Deployment | 1 | 1 | 0 | 0 | 100
Database | 1 | 1 | 0 | 0 | 100
Development | 8 | 6 | 2 | 0 | 75
Authentication | 7 | 7 | 0 | 0 | 100
API Development | 2 | 2 | 0 | 0 | 100
Course Management | 14 | 14 | 0 | 0 | 100
Testing | 3 | 2 | 1 | 0 | 67
Security | 3 | 3 | 0 | 0 | 100
Admin Panel | 3 | 3 | 0 | 0 | 100
Progress Tracking | 10 | 10 | 0 | 0 | 100
Payment System | 6 | 6 | 0 | 0 | 100
Frontend | 5 | 5 | 0 | 0 | 100